## TaskList
TASK TYPE | PRIORITY | TASK DESCRIPTION | ASSIGNEE | PLANNED START | PLANNED DAYS | ACTUAL START | ACTUAL DAYS | ACTUAL END | STATUS
Tank Elements
Player input for movement | MUST HAVE | Player input to move tank(can move left,right and jump) | Justine | 2023-01-15 | 6 | 2023-01-15 | 6 | 2023-01-21 | Completed
Render tank | MUST HAVE | Render tank in level | Justine | 2023-01-15 | 6 | 2023-01-15 | 6 | 2023-01-21 | Completed
Switch tanks | MUST HAVE | Be able to switch tanks | Justine | 2023-01-21 | 4 | 2023-01-25 |  |  | W.I.P
Respawn tank after death | MUST HAVE | Respawn tank after it fall to death or hit by projectile | Justine | 2023-01-21 | 4 | 2023-01-25 |  |  | W.I.P
Tank Movement Trails | NICE TO HAVE | Tank movement particles | Justine | 2023-02-13 | 3 |  |  |  | Not Started
Set death condition for tank | MUST HAVE | When it falls under the level or is hit by a projectile. It dies | Farhan | 2023-01-23 | 1 |  |  |  | Not Started
Collision detection for tanks | MUST HAVE | Basic collsion detection.Can detect solid objects and projectiles | Kai Zhe | 2023-01-08 | 14 |  |  |  | Not Started
Player input for shooting control for tanks | MUST HAVE | Player input to aim turrent and shoot turrent.Power based projectile. Longer player hold, further and faster it travels | Farhan | 2023-01-11 | 3 | 2023-01-14 | 4 |  | Completed
Projectile movement | MUST HAVE | Shooting logic and physics | Farhan | 2023-01-11 | 3 | 2023-01-14 | 4 |  | Completed
Projectile Collision detection | MUST HAVE | Able to detect solid objects and react accordingly(projectile will destroy Terrain/Player) | Ryan | 2023-02-13 | 7 |  |  |  | Not Started
Not Started
Level Elements
Placement of terrain | MUST HAVE | Able to choose where to place terrain, and choose it's colour | Ryan | 2023-02-02 | 14 |  |  |  | Not Started
Destruction of terrain | MUST HAVE | Upon getting hit by the hitbox of the explosion or bullet, destroy the terrain | Ryan | 2023-02-02 | 14 |  |  |  | Not Started
File saving and loading | MUST HAVE | Able to save the edited level into a file, able to pull that data and load the level into the game | Ryan | 2023-02-02 | 14 |  |  |  | Not Started
Death collider (In level) | MUST HAVE | Upon reaching the bottom of the level, player will be destroyed and the respawn will trigger | Farhan | 2023-01-24 | 1 |  |  |  | Not Started
Rubble | NICE TO HAVE | If terrain is damaged, some of it will fly off as rubble | Kai Zhe | 2023-02-04 | 10 |  |  |  | Not Started
Camera(Cinematic) | SHOULD HAVE | Camera will pan to projectile when projectile is shot | Farhan | 2023-02-08 | 3 |  |  |  | Not Started
Camera(Static) | MUST HAVE | Whole level can be seen. | Farhan | 2023-01-24 | 1 |  |  |  | Not Started
Particle System | SHOULD HAVE | A particle system to be use for projectile and explosion | Farhan | 2023-02-01 | 14 |  |  |  | Not Started
Multiple Weapon | SHOULD HAVE | Player able to switch between and use multiple weapon | Farhan | 2023-02-10 | 3 |  |  |  | Not Started
Trail System | NICE TO HAVE | Projectile leave a trail | Farhan | 2023-02-15 | 5 |  |  |  | Not Started
Score Tracker | MUST HAVE | Tell the total amount the player destroy | Justine | 2023-02-10 | 5 |  |  |  | Not Started
Turn-based system | MUST HAVE | System to detect end of player turn | Herman | 2023-02-10 | 5 |  |  |  | Not Started
Scene Manager
Scene Transistion manager | MUST HAVE | Use manager to move between scenes | Herman | 2023-01-20 | 7 |  |  |  | Not Started
Main Menu | MUST HAVE | Contain Button that exits game, go to level select menu, options menu and credits | Herman | 2023-01-08 | 4 |  |  |  | Not Started
Level Select | MUST HAVE | Contain level that player can choose | Herman | 2023-02-02 | 4 |  |  |  | Not Started
Create Placeholder level | MUST HAVE | Create Placeholder level to test out system and objects in game | Ryan | 2023-01-08 | 14 | 2023-01-10 | 10 | 2023-01-20 | Completed
Not Started
Not Started
Physic Engine
Physics engine | MUST HAVE | Objects can have forces and moments applied to them and will react with 2D Newtonian physics | Kai Zhe | 2023-01-08 | 14 |  |  |  | Not Started
Collision Detection | MUST HAVE | Ball-ball, ball-polygon, polygon-polygon collision detection | Kai Zhe | 2023-01-08 | 14 |  |  |  | Not Started
Collision Response | MUST HAVE | Collision response based on collision detection | Kai Zhe | 2023-01-08 | 14 |  |  |  | Not Started
Not Started
Not Started
Sound System
Sound component | MUST HAVE | Handle how sound files will be loaded and when to be played throughout the game | Ryan | 2023-02-20 | 5 |  |  |  | Not Started
SFX | MUST HAVE | Sound effects for player entities, player interactions with the scene and game object interactions. | Ryan | 2023-02-25 | 3 |  |  |  | Not Started
Music | SHOULD HAVE | Background music for each scene in the game | Ryan | 2023-02-25 | 3 |  |  |  | Not Started
Not Started
Art Elements
Player art | MUST HAVE | How the player will look in the game | Justine | 2023-02-16 | 7 |  |  |  | Not Started
Terrain art | MUST HAVE | The art asset for the destructable terrain | Justine | 2023-02-16 | 7 |  |  |  | Not Started
In-game UI | SHOULD HAVE | The UI for the gameplay portion of the game | Justine | 2023-02-16 | 7 |  |  |  | Not Started
Menu UI | MUST HAVE | The UI assets for the main menu/pause menu/level-editor menu | Justine | 2023-02-16 | 7 |  |  |  | Not Started
Title menu | MUST HAVE | The game title art asset | Justine | 2023-02-16 | 7 |  |  |  | Not Started
|  | Task allocated here can be under Must have, Should have,Nice to have. Just throw idea in here. | Must Have
|  | We can seperate the task to their respective Priority type | Should Have
Nice to Have

## Gantt Sheet
Team ;
Project Start | [5 empty] | 2023-01-08
Made in DigiPen | [14 empty] | 357 |  | 2023-01-08 | [6 empty] | 2023-01-15 | [6 empty] | 2023-01-22 | [6 empty] | 2023-01-29 | [6 empty] | 2023-02-05 | [6 empty] | 2023-02-12 | [6 empty] | 2023-02-19 | [6 empty] | 2023-02-26 | [6 empty] | 2023-03-05
TASK | TASK TYPE | PRIORITY | EPIC | TASK DESCRIPTION | ESTIMATED HOURS | ASSIGNEE | PLANNED START | PLANNED DAYS | PLANNED END | Grade | Perceived Hours | Feedback | ACTUAL START | ACTUAL DAYS |  | STATUS | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22 | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12 | 2023-02-13 | 2023-02-14 | 2023-02-15 | 2023-02-16 | 2023-02-17 | 2023-02-18 | 2023-02-19 | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11
[17 empty] | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S
Player input for movement | Code | 1. Must Have | Rendering | Able to render a circle at desired location | 1 | Justine | 2022-01-15 | 6 | 2022-01-21 | A | #N/A |  | 2022-01-15 | 6 |  | Completed | bar: S to F
| Code | 1. Must Have | Simulation | For a given array of cells, count the number of live cells with respect to a chosen cell | 1 |  |  |  | 0 |  | #N/A | bar: S to F
Render tank | Code | 1. Must Have | Controls | Draw circle at mouse position after clicking | 0.5 | Justine | 2022-01-15 | 6 | 2022-01-21 | A | #N/A |  | 2022-01-15 | 6 |  | Completed | bar: S to F
| Code | 1. Must Have | Simulation | Use current display to discern what the next frame should render | 1.5 |  |  |  | 0 |  | #N/A | bar: S to F
Switch tanks |  |  |  |  | 4 | Justine | 2022-01-08 | 4 | 2022-01-12 |  | #N/A |  | 2022-01-25 |  |  | W.I.P | bar: S to W
[9 empty] | 0 |  | #N/A | bar: S to W
Respawn tank after death | Code | 1. Must Have | Rendering | Able to render a rectangle at desired location | 0.5 | Justine | 2022-01-08 | 4 | 2022-01-12 |  | #N/A |  | 2022-01-25 |  |  | W.I.P | bar: S to W
| Code | 1. Must Have | Gamification | (Describe where necessary) | 1 |  |  |  | 0 |  | #N/A
Tank movement particles | [5 empty] | Justine | 2022-02-13 | 3 | [7 empty] | Not Started | bar: F to S
Set death condition for tank | Code | 1. Must Have | Controls | Buttons need to react on click. | 1 | Farhan | 2022-01-23 | 1 | 2022-01-24 | F | #N/A |  |  |  |  | Not Started | bar: M
| Code | 3. Could Have | Gamification | (Describe where necessary) | 1 |  |  |  | 0 |  | #N/A
Set Collision for tank | Code | 1. Must Have | Controls | It should display in text the current shape being drawn. Clicking on it should cycle between "Circle" and "Square" shapes being drawn. | 1 | Khai Zeh | 2022-02-02 | 3 | 2022-02-05 |  | #N/A |  |  |  |  | Not Started | bar: T to S
| Code | 4. Won't Have | Gamification | (Describe where necessary) | 1 |  |  |  | 0 |  | #N/A
Player input for shooting control for tanks | Code | 1. Must Have | Controls | It should display in text the current colour used for drawing the shape. Clicking on the button should cycle between Red, Green and Blue colours for the shape drawn. | 1 | Farhan | 2022-01-11 | 3 | 2022-01-14 |  | #N/A |  | 2022-01-14 | 3 |  | Completed | bar: W to F
| Audio | 3. Could Have | Gamification | (Describe where necessary) | 4 |  |  |  | 0 |  | #N/A | bar: S to M
Projectile movement | [5 empty] | Farhan | 2022-01-11 | 3 | 2022-01-14 |  | #N/A |  | 2022-01-14 | 3 |  | Completed | bar: W to F
| Audio | 3. Could Have | Gamification | (Describe where necessary) | 4 |  |  |  | 0 |  | #N/A | bar: S to M
Projectile Collision detection | Code | 1. Must Have | Rendering | Draw grid using rectangles, based on defined number of columns and rows and window dimensions | 0.5 | Ryan | 2022-02-13 | 7 | 2022-02-20 |  | #N/A |  |  |  |  | Not Started | bar: M to M
| Art | 4. Won't Have | Gamification | (Describe where necessary) | 8 |  |  |  | 0 |  | #N/A
Placement of terrain | Art | 3. Could Have | Gamification | (Describe where necessary) | 4 | Ryan | 2022-02-02 | 14 | 2022-02-16 |  | #N/A |  |  |  |  | Not Started | bar: T to T
| Art | 3. Could Have | Gamification | (Describe where necessary) | 4 |  |  |  | 0 |  | #N/A
Destruction of terrain | Code | 2. Should Have | Gamification | (Describe where necessary) | 1 | Ryan | 2022-02-02 | 14 | 2022-02-16 |  | #N/A |  |  |  |  | Not Started | bar: T to W
| Code | 2. Should Have | Gamification | (Describe where necessary) | 4 |  |  |  | 0 |  | #N/A
File saving and loading | Code | 1. Must Have | Gamification | (Describe where necessary) | 8 | Ryan | 2022-02-02 | 14 | 2022-02-16 |  | #N/A |  |  |  |  | Not Started | bar: T to W
| Code | 2. Should Have | Gamification | (Describe where necessary) | 8 |  |  |  | 0 |  | #N/A
Death collider (In level) | Code | 2. Should Have | Gamification | (Describe where necessary) | 8 | Farhan | 2022-01-24 | 1 | 2022-01-25 |  | #N/A |  |  |  |  | Not Started | bar: T
| Code | 2. Should Have | Gamification | (Describe where necessary) | 1 |  |  |  | 0 |  | #N/A
Rubble | Code | 2. Should Have | Gamification | (Describe where necessary) | 1 | Khai Zeh | 2022-02-04 | 10 | 2022-02-14 |  | #N/A |  |  |  |  | Not Started | bar: S to T
| Art | 3. Could Have | Gamification | (Describe where necessary) | 4 |  |  |  | 0 |  | #N/A
Camera(Cinematic) | Audio | 3. Could Have | Gamification | (Describe where necessary) | 4 | Farhan | 2022-02-08 | 3 | 2022-02-11 |  | #N/A |  |  |  |  | Not Started | bar: W to F
| Audio | 3. Could Have | Gamification | (Describe where necessary) | 4 |  |  |  | 0 |  | #N/A
Camera(Static) | [5 empty] | Farhan | 2022-01-24 | 1 | 2022-01-25 |  | #N/A |  |  |  |  | Not Started | bar: T
[9 empty] | 0 |  | #N/A
Particle System | [5 empty] | Farhan | 2022-02-01 | 14 | 2022-02-15 |  | #N/A |  |  |  |  | Not Started | bar: W to W
[9 empty] | 0 |  | #N/A
Multiple Weapon | [5 empty] | Farhan | 2022-02-10 | 3 | 2022-02-13 |  | #N/A |  |  |  |  | Not Started | bar: F to S
[9 empty] | 0 |  | #N/A
Trail System | [5 empty] | Farhan | 2022-02-15 | 5 | 2022-02-20 |  | #N/A |  |  |  |  | Not Started | bar: W to S
[9 empty] | 0 |  | #N/A
Score Tracker | [5 empty] | Justine | 2022-01-08 | 5 | 2022-01-13 |  | #N/A |  |  |  |  | Not Started | bar: S to T
[9 empty] | 0 |  | #N/A
Turn-based system | [5 empty] | Herman | 2022-02-10 | 5 | 2022-02-15 |  | #N/A |  |  |  |  | Not Started | bar: F to T
[9 empty] | 0 |  | #N/A
Scene Transistion manager | [5 empty] | Herman | 2022-01-20 | 7 | 2022-01-27 |  | #N/A |  |  |  |  | Not Started | bar: M to S
[9 empty] | 0 |  | #N/A
Main Menu | [5 empty] | Herman | 2022-01-08 | 4 | 2022-01-12 |  | #N/A |  |  |  |  | Not Started | bar: S to W
[9 empty] | 0 |  | #N/A
Level Select | [5 empty] | Herman | 2022-02-02 | 4 | 2022-02-06 |  | #N/A |  |  |  |  | Not Started | bar: T to S
Create Placeholder level | [5 empty] | Ryan | 2022-01-08 | 14 |  |  |  |  | 2022-01-10 | 10 |  | Completed | bar: S to S
[9 empty] | 0 |  | #N/A | bar: T to W
Physics engine | [5 empty] | Khai Zeh | 2022-01-08 | 14 | 2022-01-22 |  | #N/A |  | 2022-01-08 | 7 |  | W.I.P | bar: S to S
[9 empty] | 0 |  | #N/A
Collision Detection | [5 empty] | Khai Zeh | 2022-01-08 | 14 | 2022-01-22 |  | #N/A |  | 2022-01-08 | 14 |  | W.I.P | bar: S to S
[9 empty] | 0 |  | #N/A
Collision Response | [5 empty] | Khai Zeh | 2022-01-08 | 14 | 2022-01-22 |  | #N/A |  | 2022-01-08 | 14 |  | W.I.P | bar: S to S
[9 empty] | 0 |  | #N/A
Sound component | [5 empty] | Ryan | 2022-02-20 | 5 | 2022-02-25 |  | #N/A |  |  |  |  | Not Started | bar: F to T; M to F
[9 empty] | 0 |  | #N/A
SFX | [5 empty] | Ryan | 2022-02-25 | 3 | 2022-02-28 |  | #N/A |  |  |  |  | Not Started | bar: W to F; S to M
[9 empty] | 0 |  | #N/A
Music | [5 empty] | Ryan | 2022-02-25 | 3 | 2022-02-28 |  | #N/A |  |  |  |  | Not Started | bar: W to F; S to M
[9 empty] | 0 |  | #N/A
Player art | [5 empty] | Justine | 2022-02-16 | 7 | 2022-02-23 |  | #N/A |  |  |  |  | Not Started | bar: T to W
[9 empty] | 0 |  | #N/A
Terrain art | [5 empty] | Justine | 2022-02-16 | 7 | 2022-02-23 |  | #N/A |  |  |  |  | Not Started | bar: T to W
[9 empty] | 0 |  | #N/A
In-game UI | [5 empty] | Justine | 2022-02-16 | 7 | 2022-02-23 |  | #N/A |  |  |  |  | Not Started | bar: T to W
[9 empty] | 0 |  | #N/A
Menu UI | [5 empty] | Justine | 2022-02-16 | 7 | 2022-02-23 |  | #N/A |  |  |  |  | Not Started | bar: T to W
[9 empty] | 0 |  | #N/A
Title menu | [5 empty] | Justine | 2022-02-16 | 7 | 2022-02-23 |  | #N/A |  |  |  |  | Not Started | bar: T to W
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
[9 empty] | 0 |  | #N/A
Plan
Actual